## Slide 1
INFO DAN
MATRICA LOGIČKOG OKVIRA
Prekogranični program
Srbija – Crna Gora
Notes: <number>

## Slide 2: MATRICA LOGIČKOG OKVIRA
Aneks “C” Prijavnog obrasca
Excel tabela
Mora biti priložena uz Prijavni obrazac u štampanoj verziji, kao i u elektronskom formatu

## Slide 3
Logički okvir kao pristup
upravljanju projektima
Pristup logičkog okvira (Logical Framework Approach)
  Analitički proces
  Set alata za
    planiranje i
    upravljanje projektima
Logička matrica kao jedan od proizvoda tog procesa (Logical Framework Matrix)
  Tabela koja sadrži:
    Hijerarhiju ciljeva projekta
    Ključne spoljne faktore koji utiču na projekat
    Načine na koji će se pratiti sprovođenje i ocjenjivati projekat
    Osnove za utvrđivanje potrebnih resursa i proračuna

## Slide 4: Koraci u kreiranju matrice logičkog okvira
Analiza situacije
Analiza činioca – stekeholder
Analiza problema
Analiza ciljeva
Analiza alternativa
Planiranje aktivnosti

## Slide 5: LOGIČKI OKVIR
Opšti cilj
Specifični
cilj
Pretpostavke
Pretpostavke
Aktivnosti
Pretpostavke
Preduslovi
Indikatori
Izvori
provjere
Indikatori
Izvori
provjere
Rezultat
Indikatori
Izvori
provjere
Sredstva
Troškovi

## Slide 6: Matrica logičkog okvira
Sažet tabelarni prikaz projekta koji služi:
  Kvalitetnom i logičnom planiranju i definisanju projekta
  Jasnoj prezentaciji projekta (donatorima i ostalim činiocima)
  Ocjeni kao i praćenju sprovođenja projekta

## Slide 7: LOGICAL FRAMEWORK FOR THE PROJECT
 | Intervention logic | Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall objectives | What are the overall broader objectives to which the action will contribute? | What are the key indicators related to the overall objectives? | What are the sources of information for these indicators? | 
Specific objective | What specific objective is the action intended to achieve to contribute to the overall objectives? | Which indicators clearly show that the objective of the action has been achieved? | What are the sources of information that exist or can be collected? What are the methods required to get this information? | Which factors and conditions outside the Beneficiary's responsibility are necessary to achieve that objective? (external conditions) Which risks should be taken into consideration?
Expected results | The results are the outputs envisaged to achieve the specific objective. What are the expected results? (enumerate them) | What are the indicators to measure whether and to what extent the action achieves the expected results? | What are the sources of information for these indicators? | What external conditions must be met to obtain the expected results on schedule?
Activities | What are the key activities to be carried out and in what sequence in order to produce the expected results? (group the activities by result) | Means: What are the means required to implement these activities, e. g. personnel, equipment, training, studies, supplies, operational facilities, etc. | What are the sources of information about action progress? Costs What are the action costs? How are they classified? (breakdown in the Budget for the Action) | What pre-conditions are required before the action starts? What conditions outside the Beneficiary's direct control have to be metfor the implementation of the planned activities?

## Slide 8: Redosljed popunjavanja logičke matrice
Aktivnosti
Rezultati
Specifični cilj
Opšti ciljevi
1
Pretpostavke
Izvori provjere
Objektivno provjerljivi indikatori
Opis projekta
2
4
3
8
10
12
9
11
13
7
6
5

## Slide 9
Hvala i srećno!